## Summary
Buildora Cost Tracker
Project Information
Project ID | 347f60e5-074f-4131-9318-38488e09b72a
Project Name | Mega
Status | processing
Generated | 2026-04-24 09:33 UTC
Compliance Summary
Compliance Score | 0.0%
Status | FAIL
Missing Documents | 22

## Cost Breakdown
Category | Budgeted (RM) | Actual (RM) | Variance (RM) | Variance (%)
Materials | 150000 | 145000 | -5000 | -333%
Labor | 200000 | 210000 | 10000 | 500%
Equipment | 80000 | 82000 | 2000 | 250%
Permits & Fees | 30000 | 28000 | -2000 | -667%
Contingency | 40000 | 35000 | -5000 | -1250%
TOTAL

## Timeline
Milestone | Planned Date | Actual Date | Status | Delay (Days)
Project Kickoff | 2026-01-01 | 2026-01-01 | Completed | 0
Design Approval | 2026-02-15 | 2026-02-20 | Completed | 5
Permit Submission | 2026-03-01 | 2026-03-05 | Completed | 4
Construction Start | 2026-04-01 | Pending | In Progress | 0
Phase 1 Complete | 2026-06-30 | Pending | Pending | 0