# PROJECT SCHEDULE AND MILESTONES

Project Name: Eco-Green Residences @ Cyberjaya

Project No.: EG-RC-2026-001

Date: 1st May 2026

## 1. PROJECT OVERVIEW

This document outlines the key milestones and overall schedule for the "Eco-Green Residences @ Cyberjaya" project. The project involves the construction of a 20-story eco-friendly residential building with 250 units, common facilities, and landscaping. The project is managed by Prima Konstruk Sdn. Bhd. for EcoBuild Developments Sdn. Bhd.

- Commencement Date: 2026-05-01

- Scheduled Completion Date: 2028-04-30

- Total Duration: 24 Months

## 2. KEY MILESTONES

The following table details the critical milestones for the project, including their baseline scheduled dates. These milestones are crucial for tracking project progress and will be monitored by the Buildora AI system.

| Milestone ID | Milestone Description | Scheduled Date (Baseline) | Status for Testing |
| --- | --- | --- | --- |
| M-01 | Foundation Works Completion | 2026-08-31 | On Track |
| M-02 | Structural Frame (Level 10) Completion | 2027-03-15 | Slightly Delayed (Actual: 2027-03-20) |
| M-03 | Building Enclosure Completion | 2027-10-31 | On Track |
| M-04 | Internal Finishes & M&E First Fix Completion | 2028-01-31 | On Track |
| M-05 | CCC Application & Handover | 2028-04-30 | On Track |

Note for Testing: Milestone M-02 is intentionally set to be slightly delayed (5 days past baseline) to simulate a scenario where Agent B (Schedule Monitor) should detect a delay and trigger an alert.

## 3. PAYMENT SCHEDULE

The payment schedule below outlines the planned disbursement of funds based on project progress. These payment dates and amounts are critical for financial monitoring and will be used to detect potential cost variances by the Buildora AI system.

| Payment No. | Description | Percentage of Contract Sum | Amount (RM) | Due Date |
| --- | --- | --- | --- | --- |
| P-01 | Mobilization | 10% | 7,500,000.00 | 2026-05-15 |
| P-02 | Foundation Works Completion | 20% | 15,000,000.00 | 2026-09-15 |
| P-03 | Structural Frame Completion | 30% | 22,500,000.00 | 2027-04-15 |
| P-04 | Building Enclosure Completion | 20% | 15,000,000.00 | 2027-11-15 |
| P-05 | Internal Finishes & M&E First Fix | 15% | 11,250,000.00 | 2028-02-15 |
| P-06 | Final Payment (Retention Release) | 5% | 3,750,000.00 | 2028-05-30 |

## 4. PROJECT TEAM

- Project Manager (Contractor): Ir. Siti Nurhaliza Binti Ahmad

- Project Director (Client): Mr. Tan Kian Meng

- Safety & Health Officer: Mr. Kamal Bin Hassan

## 5. DOCUMENT CONTROL

| Field | Detail |
| --- | --- |
| Document Version | 1.0 |
| Prepared By | Manus AI |
| Date Prepared | 2026-04-25 |
| Last Revised | 2026-04-25 |